## New Targets
|  | Wk 0 - 6 Apr 2020 | Wk 1 - 13 Apr 2020 | Wk 2 - 20 Apr 2020 | Wk 3 - 27 Apr 2020 | Wk 4 - 4 May 2020
Activities | Owner |  |  | [Surge Week] | [Surge Week] | [Surge Week] | Comments
NIH S, M Moulds -> One-Piece 13 April 2020 onwards | Josh/Vahid/William |  | Progress
Montana S, M | Brandon/Thomas | Done
NIH S, M Inlays | Josh/Vahid | Done
NIOSH Testing -> Proof of Concept 13 April 2020 | Andrew/Vahid/Will | Done
Choose 1 Mask | Thomas/Will |  | NIH one-piece & Manitoba
Build Simple Silicone Mask Mould and Cast 13 Apri 2020 | Thomas/Brandon |  | Progress
Build NIH Medium and Small one-piece with adapter Mould and Cast 13 April 2020 | Josh/Vahid |  | Progress
OHSA 9 CFR 1910.134 Fit Testing protocol on 14-15 Apr 2020 on volunteers Human Factors | Andrew/Carla |  | Progress
Funding Comparison | Will/GLIA | Not started | Not started
Health Canada contact for emergency devide approval | Carla/Will/GLIA | Not started | Not started
Obtain REB | Carla/Binu/Will | Progress | Progress
Report back to SickKids and UHN COVID-PPE Leads | Thomas/Will | Not started | Not started
Funding Proposal to UHN (dependent on report findings) | Carla/Will | Not started | Not started
Develop Adapter with smaller connection to ROXON for NIH and Montana | Josh | Done
Obtain Acess to Ontario Power Generation testing facilities | Leah (Queen's) | Progress | Progress
Candidate Refining [Josh/Vahid/Brandon/Taylor] 16 Apr | Josh/Vahid/Brandon/Taylor | Done
Arrange 2nd NIOSH Testing for Refined Options | Josh/Vahid/Brandon/Taylor | Not started | Not started
Develop Decontamination Protocols | Vahid/GLIA | Not started
Need GLIA's help with MDEL or APIL's MDEL [Carla/Azad/Carrie Wakem] | Carla/Azad/GLIA | TBC
Obtain Health Canada approval | Andrew/Azad/GLIA | TBC
Reach Industry Partners for upscale of Silicone Moulds, Bodies | William/Brian | TBC
Confirm Filtering solution from Woodbridge (if filter passes testing) | William/Carla | Stopped Pursuit
Bitrex Testing for 3 sizes of 1 type | Andrew/Queen's Un.
Bitrex Testing UHN | William/Azad
Manufacture First 50 units | William/Brian
Test first 50 Units | Vahid/GLIA
Manufacture First 200 units | William/Brian
Test batches | Vahid/GLIA
Develop Website | ?
Develop Distributition Logistics [GLIA/Will] | William/GLIA
Iformation Dissemination | Carla/Andrew
Manufacture 1000 units [ | William/Brian
Supply UHN Stock for stop-gap | William/Azad
Project wind-down | William/GLIA
Write-up Project finalization [Andrew/Carla/Will] | Carla/Andrew/William
Note on B10: WN: Joe Caffazo OHS or OS & EH Susy Hota

## Sheet1
|  | Wk 0 - 6 Apr 2020 | Wk 1 - 13 Apr 2020 | Wk 2 - 20 Apr 2020 | Wk 3 - 27 Apr 2020 | Wk 4 - 4 May 2020
Activities | Owner |  |  | [Surge Week] | [Surge Week] | [Surge Week] | Comments
NIH S, M Moulds | William
Montana S, M
NIH S, M Inlays
NIOSH Testing
Choose 3 Mask bodies [ | William/Andrew/Brandon/Josh/Vahid
Develop Adapter withsmaller connection to ROXON for NIH and Montana | Josh
Bitrex Testing for 3 sizes of 1 type | Andrew/Queen's Un.
Bitrex Testing UHN | William/Azad
Obtain REB | Carla
Obtain Acess to Ontario Power Generation testing facilities | Leah (Queen's)
Candidate Refining [Josh/Vahid/Brandon/Taylor] 16 Apr | Josh/Vahid/Brandon/Taylor
Arrange 2nd NIOSH Testing for Refined Options | Josh/Vahid/Brandon/Taylor
Develop Decontamination Protocols | Vahid/GLIA
Need GLIA's help with MDEL or APIL's MDEL [Carla/Azad/Carrie Wakem]
Obtain Health Canada approval | Azad/William/GLIA
Reach Industry Partners for upscale of Silicone Moulds, Bodies | William/Brian
Confirm Filtering solution from Woodbridge (if filter passes testing) | William/Carla
Manufacture First 40 units | William/Brian
Test first 40 Units | Vahid/GLIA
Manufacture First 200 units | William/Brian
Test batches | Vahid/GLIA
Develop Website | ?
Develop Distributition Logistics [GLIA/Will] | William/GLIA
Iformation Dissemination | Carla/Andrew
Manufacture 1000 units [ | William/Brian
Supply UHN Stock for stop-gap | William/Azad
Project wind-down | William/GLIA
Write-up Project finalization [Andrew/Carla/Will] | Carla/Andrew/William